Appliance Warehouse Case Study

Jesse Xiong

September 13, 2024

Opportunity Statement: Currently, Appliance Warehouse (AW) relies on external service providers for appliance repairs. This arrangement often leads to delays, inconsistent service quality, and customer dissatisfaction. Additionally, customers who are not satisfied with the repair service might opt to purchase new appliances elsewhere, leading to a potential loss of sales for AW.

Impact:

- Customer Dissatisfaction: Lack of control over repair quality and timing negatively impacts customer satisfaction.

- Operational Inefficiencies: Fragmented process with external service providers complicates scheduling and parts management.

- Lost Revenue: Potential loss of sales if customers choose to replace appliances instead of repairing them due to service inefficiencies.

My Ideal state for this service is that the establishment of an in-house Service Department will integrate appliance repair services with AW’s existing sales and parts departments. This integration will streamline operations, improve customer satisfaction by providing reliable and timely repairs, and increase potential sales by offering a comprehensive solution for appliance needs. By managing repairs internally, AW can enhance customer loyalty and capture additional revenue.

AW’s Current mission statement: "We are your one-stop shop for all of your home appliances and parts!"

My suggested statement modification: "At Appliance Warehouse, we are your one-stop shop for home appliances, parts, and expert repair services. Our mission is to provide exceptional service and quality solutions to meet all your appliance needs, ensuring customer satisfaction and convenience."

The modified statement includes "expert repair services" to accurately reflect the addition of a new service department, emphasizing AW's comprehensive offerings. This update better communicates AW’s commitment to providing complete solutions and exceptional customer service, aligning with the company's expanded role as a one-stop shop for all appliance needs.

Appliance Warehouse Staffing

Parts Department – Purchasing, inventory control, sales

- Director: Maddox Farley

- Sales Staff: Tyler Cummings, Steve Dawson, Amelia Warner

- Purchasing: Celia Martel, Joe Perez

- Inventory/Warehouse: Ben Cooke, Melissa Benedict, Matt Jones

Appliance Department – Sales of new appliances in 4 departments

- Director: Sonia Lopez

- Large Kitchen Appliance department: Mike Nelson (Manager), Jessica Scott, Rachel Evans, Justin Cooper

- Laundry Appliance Department: Tina Turner (Manager), Mackenzie Scott, James Wright

- Audio/Visual Department: Samantha Campbell (Manager), Tim Reynolds, Tracey Oliver

- Small Appliance Department: Peter Parker (Manager), Ken Howell, Marti Castillo

Service Department:

- Service Manager: Emily Johns

- Technicians: Liam Henson, Mark Robles, Lee Wong

- Appointment Setters: Lisa Shields, Jake Meyers

- Equipment and Parts: Rhonda Patel

Store Wide Cashiers:

- Manager: Abby Franklin

- Cashiers: Nancy Richards, Joy Vasquez, David Goodman, Paul Patton, Maria Nunez

Administrative Roles:

- Owner: Mae Roth (Store Manager reports to this role)

- Store Manager: Alan Marks (All department heads and assistant manager reports to this role)

- Store Assistant Manager: Ali Miranda (Admin roles report to assistant manager)

- Admin Assistant to Store Manager: Tim Stafford

- HR Specialist: Joey Booker

- Accounting, Payroll, Accounts Payable/Receivable: Doug Dorsey, Tia Carey

- IT Department: Carlie Davis (Manager), Tony Barlett, Meredith Parks, Logan Ader

Work Breakdown Structure (WBS)

1. Planning Phase

- 1.1 Define Project Scope

  - Start Date: 2024-09-20

  - End Date: 2024-09-22

- 1.2 Initial Stakeholder Meeting

  - Start Date: 2024-09-23

  - End Date: 2024-09-23

- 1.3 Feasibility Study

  - Start Date: 2024-09-24

  - End Date: 2024-09-26

- 1.4 Write Project Charter

  - Start Date: 2024-09-27

  - End Date: 2024-09-28

- 1.5 Obtain Approval for Project Charter

  - Start Date: 2024-09-29

  - End Date: 2024-09-30

2. Analysis Phase

- 2.1 Analyze Current Processes

  - Start Date: 2024-10-01

  - End Date: 2024-10-05

- 2.2 Identify Technology Needs

  - Start Date: 2024-10-06

  - End Date: 2024-10-10

- 2.3 Research Industry Standards

  - Start Date: 2024-10-11

  - End Date: 2024-10-15

- 2.4 Review Best Practices

  - Start Date: 2024-10-16

  - End Date: 2024-10-18

- 2.5 Prepare Analysis Report

  - Start Date: 2024-10-19

  - End Date: 2024-10-21

3. Design Phase

- 3.1 Define System Requirements

  - Start Date: 2024-10-22

  - End Date: 2024-10-26

- 3.2 Design System Architecture

  - Start Date: 2024-10-27

  - End Date: 2024-10-31

- 3.3 Develop Data Flow Diagrams (DFD)

  - Start Date: 2024-11-01

  - End Date: 2024-11-04

- 3.4 Design User Interfaces (UI) and Prototyping

  - Start Date: 2024-11-05

  - End Date: 2024-11-11

- 3.5 Develop Integration Plan

  - Start Date: 2024-11-12

  - End Date: 2024-11-14

4. Implementation Phase

- 4.1 System Setup and Configuration

  - Start Date: 2024-11-15

  - End Date: 2024-11-22

- 4.2 Data Migration

  - Start Date: 2024-11-23

  - End Date: 2024-11-29

- 4.3 Staff Training

  - Start Date: 2024-11-30

  - End Date: 2024-12-04

- 4.4 System Testing and Debugging

  - Start Date: 2024-12-05

  - End Date: 2024-12-11

- 4.5 Go-Live and Post-Deployment Support

  - Start Date: 2024-12-12

  - End Date: 2024-12-18

5. Security/Maintenance Phase

- 5.1 Conduct Security Assessment

  - Start Date: 2024-12-19

  - End Date: 2024-12-23

- 5.2 Implement Access Controls

  - Start Date: 2024-12-24

  - End Date: 2024-12-28

- 5.3 Data Encryption Setup

  - Start Date: 2024-12-29

  - End Date: 2024-12-31

- 5.4 Develop Backup and Recovery Plan

  - Start Date: 2025-01-02

  - End Date: 2025-01-04

- 5.5 Schedule Ongoing Security Audits

  - Start Date: 2025-01-05

  - End Date: 2025-01-07

Cost Estimates and Duration

Costs for In-House Development:

- Database Development

  - Cost per Hour: $60

  - Duration: Database Design (5 days), Database Build (10 days)

  - Total Cost: Database Design = 5 days x 8 hours/day x $60/hour = $2,400 Database Build = 10 days x 8 hours/day x $60/hour = $4,800

- Web Developers / App Developers

  - Cost per Hour: $75

  - Duration:

    - Design of Report: 2 days

    - Design of Data Entry Page: 2 days

    - Design of Static Text Page: 1 day

    - Build of Report: 1 day

    - Build of Data Entry Page: 1 day

    - Build of Static Text Page: 1 day

    - Connection to Separate System or Database: 8 days

  - Total Cost:

    - Design of Report = 2 days x 8 hours/day x $75/hour = $1,200

    - Design of Data Entry Page = 2 days x 8 hours/day x $75/hour = $1,200

    - Design of Static Text Page = 1 day x 8 hours/day x $75/hour = $600

    - Build of Report = 1 day x 8 hours/day x $75/hour = $600

    - Build of Data Entry Page = 1 day x 8 hours/day x $75/hour = $600

    - Build of Static Text Page = 1 day x 8 hours/day x $75/hour = $600

    - Connection to Separate System = 8 days x 8 hours/day x $75/hour = $4,800

- UX Designers

  - Cost per Hour: $60

  - Duration:

    - Design of Report: 2 days

    - Design of Data Entry Page: 2 days

    - Design of Static Text Page: 1 day

  - Total Cost:

    - Design of Report = 2 days x 8 hours/day x $60/hour = $960

    - Design of Data Entry Page = 2 days x 8 hours/day x $60/hour = $960

    - Design of Static Text Page = 1 day x 8 hours/day x $60/hour = $480

- Business Analyst

  - Cost per Hour: $50

  - Duration:

    - Analysis Work: 20 days

  - Total Cost:

    - Analysis Work = 20 days x 8 hours/day x $50/hour = $8,000

- Trainers

  - Cost per Hour: $50

  - Duration:

    - Training: 5 days

  - Total Cost:

    - Training = 5 days x 8 hours/day x $50/hour = $2,000

- Cybersecurity Specialists

  - Cost per Hour: $90

  - Duration:

    - Cybersecurity Work: 10 days

  - Total Cost:

    - Cybersecurity Work = 10 days x 8 hours/day x $90/hour = $7,200

- System Admin

  - Cost per Hour: $70

  - Duration:

    - Connection to Separate System or Database: 8 days

  - Total Cost:

    - Connection to Separate System = 8 days x 8 hours/day x $70/hour = $4,480

- Equipment Costs

  - Servers: $2,500

  - Routers: $200

Expected Monthly Maintenance

- Development: 2 days

- System Admin: 3 days

- Training: 1 day

List of Possible Risks

- Scope Creep: Unplanned changes that increase the project scope.

- Budget Overruns: Exceeding the initial budget due to unexpected costs.

- Technical Challenges: Issues that arise during the design or implementation phases.

- Resource Availability: Key team members or resources may be unavailable.

- Security Vulnerabilities: Potential risks to system security.

- Data Migration Issues: Problems during data migration affecting data integrity.

- User Resistance: Difficulty in adapting to the new